## Gantt Chart
Task ID | Task Name | Owner | Start | End | Duration (days) | % Complete | Dependencies | Notes
1 | Literature Review | Student | 2024-01-15 | 2024-02-15 | 31 | 100 |  | EMH, ML, DL references
2 | Data Acquisition | Student | 2024-02-01 | 2024-02-28 | 27 | 100 | 1 | Alpha Vantage + yfinance
3 | Feature Engineering | Student | 2024-02-15 | 2024-03-15 | 29 | 100 | 2 | Technical indicators, regime labels
4 | Iteration 1 - Linear Baseline | Student | 2024-03-01 | 2024-03-15 | 14 | 100 | 3 | Persistence, Linear, Logistic
5 | Iteration 1.1 - SVR | Student | 2024-03-10 | 2024-03-20 | 10 | 100 | 4 | RBF kernel SVR
6 | Iteration 2 - Tree Ensembles | Student | 2024-03-15 | 2024-04-01 | 17 | 100 | 4 | RF, XGBoost, SVM
7 | Iteration 2.1 - LightGBM | Student | 2024-03-25 | 2024-04-10 | 16 | 80 | 6 | Gradient boosted trees
8 | Iteration 3 - LSTM | Student | 2024-04-01 | 2024-04-20 | 19 | 60 | 6 | Recurrent neural network
9 | Iteration 4 - Transformer | Student | 2024-04-15 | 2024-05-05 | 20 | 40 | 8 | Attention mechanism
10 | Iteration 5 - Meta-Ensemble | Student | 2024-05-01 | 2024-05-20 | 19 | 20 | 9 | Stacked models + risk layer
11 | 20-Stock Robustness | Student | 2024-05-10 | 2024-05-25 | 15 | 0 | 10 | S&P 500 sample validation
12 | Results & Plots | Student | 2024-05-20 | 2024-06-05 | 16 | 0 | 11 | Tables, heatmaps, residuals
13 | Monte Carlo Risk | Student | 2024-05-25 | 2024-06-10 | 16 | 0 | 10 | Equity curve stress test
14 | Final Report | Student | 2024-06-01 | 2024-06-20 | 19 | 0 | 12,13 | Dissertation write-up
15 | Viva Preparation | Student | 2024-06-15 | 2024-06-30 | 15 | 0 | 14 | Defense slides