## Risk Register
ID | Risk | Likelihood | Impact | Owner | Mitigation | Status | Last Updated
R1 | API downtime/rate limits | Medium | High | Student | Use yfinance fallback; cache data locally; respect pause intervals | Mitigated | 2024-01-20
R2 | Look-ahead/data leakage | High | Critical | Student | Strict walk-forward validation; no future data in features; code review | Open | 2024-02-01
R3 | Compute/resource limits | Medium | Medium | Student | Use Google Colab GPU; optimize batch sizes; early stopping | Mitigated | 2024-02-15
R4 | Time overrun | Medium | High | Student | Prioritize core iterations; drop optional extensions if needed | Monitoring | 2024-03-01
R5 | Poor generalization | High | High | Student | Multiple assets; walk-forward splits; regularization; ensemble methods | Monitoring | 2024-03-15