## Supervisor Meetings
Date | Attendees | Agenda/Topics | Decisions/Actions | Owner | Due Date | Notes
2024-01-15 | Student, Supervisor | Project scope, literature review plan | Confirm EMH/ML focus; draft lit review outline | Student | 2024-01-25 | Initial kick-off
2024-02-01 | Student, Supervisor | Data sources, Alpha Vantage API | Proceed with AV+yfinance; document fallback logic | Student | 2024-02-10 | API key obtained
2024-02-15 | Student, Supervisor | Feature engineering approach | Include technical indicators, regime labels; avoid leakage | Student | 2024-03-01 | Walk-forward design agreed